## AESS - Dev
AESS System Development
| Project Completion |  |  |  |  | Project Start: | 2026-11-07
[6 empty] | Display Week: | 2
TASK No. | ACTIVITY | ASSIGNED TO | PROGRESS | SUPPORT FEEDBACK | START | DAYS | END
1 | Project Initiation |  |  |  | 2026-03-01 |  | 2026-12-13
1.2 | Capstone System Development — AESS (Alumni Engagement & Support System)
1.2.1 | Alumni Portal (Frontend)
1.2.1.1 | Authentication UI (Login / Register / Forgot Password) | RALPH | 100% |  | 2026-03-01 |  | 2026-03-05
1.2.1.2 | Alumni eligibility check & registration (roster-linked) | RALPH | 100% |  | 2026-03-06 |  | 2026-03-10
1.2.1.3 | Alumni onboarding wizard | RALPH | 100% |  | 2026-03-11 |  | 2026-03-14
1.2.1.4 | Alumni Home dashboard | RALPH | 100% |  | 2026-03-15 |  | 2026-03-18
1.2.1.5 | Events (browse, RSVP, comments, calendar) | RALPH | 100% |  | 2026-03-19 |  | 2026-03-24
1.2.1.6 | Tracer & Surveys (CHED GTS form + custom surveys) | RALPH | 100% |  | 2026-03-25 |  | 2026-04-05
1.2.1.7 | Job board (browse, interest, recommendations) | RALPH | 100% |  | 2026-04-06 |  | 2026-04-12
1.2.1.8 | Community Forum (topics, replies, tags) | RALPH | 100% |  | 2026-04-13 |  | 2026-04-18
1.2.1.9 | Messaging (alumni <-> admin, attachments) | RALPH | 100% |  | 2026-04-19 |  | 2026-04-24
1.2.1.10 | Announcements (read / targeted audience) | RALPH | 100% |  | 2026-04-25 |  | 2026-04-28
1.2.1.11 | Profile, password change & Alumni ID card | RALPH | 100% |  | 2026-04-29 |  | 2026-05-05
1.2.1.12 | Feedback submission & tracking | RALPH | 100% |  | 2026-05-06 |  | 2026-05-08
1.2.1.13 | AI Assistant (alumni guidance chatbot) | RALPH | 100% |  | 2026-05-09 |  | 2026-05-12
1.2.1.14 | Notifications center & preferences (in-app / push) | RALPH | 80% |  | 2026-05-13 |  | 2026-05-18
1.3 | Admin Portal (Frontend)
1.3.1 | Admin dashboard shell (sidebar, KPIs, activity) | RALPH | 100% |  | 2026-05-19 |  | 2026-05-26
1.3.2 | Alumni Directory & member detail (roster) | RALPH | 100% |  | 2026-05-27 |  | 2026-06-05
1.3.3 | Surveys (editor, responses, analytics, export) | RALPH | 100% |  | 2026-06-06 |  | 2026-06-18
1.3.4 | Reports & Analytics (GTS charts, presets, CHED compare) | RALPH | 100% |  | 2026-06-19 |  | 2026-06-30
1.3.5 | Program Insights / DSS (findings, plan, proof, outcomes) | RALPH | 100% |  | 2026-07-01 |  | 2026-07-20
1.3.6 | Events management (CRUD, RSVP, comments) | RALPH | 100% |  | 2026-07-21 |  | 2026-07-28
1.3.7 | Announcements management (audience, email delivery) | RALPH | 100% |  | 2026-07-29 |  | 2026-08-04
1.3.8 | Forum moderation | RALPH | 100% |  | 2026-08-05 |  | 2026-08-08
1.3.9 | Admin messaging inbox | RALPH | 100% |  | 2026-08-09 |  | 2026-08-12
1.3.10 | Job postings management & career insights | RALPH | 100% |  | 2026-08-13 |  | 2026-08-18
1.3.11 | Activity / audit logs viewer | RALPH | 100% |  | 2026-08-19 |  | 2026-08-21
1.3.12 | Archives (events / jobs / surveys) | RALPH | 100% |  | 2026-08-22 |  | 2026-08-24
1.3.13 | Feedback management & responses | RALPH | 100% |  | 2026-08-25 |  | 2026-08-27
1.3.14 | AI Assistant (admin) | RALPH | 100% |  | 2026-08-28 |  | 2026-08-29
1.3.15 | CHED GTS PDF / fillable export | RALPH | 100% |  | 2026-08-30 |  | 2026-09-05
1.4 | Backend & Platform (Supabase)
1.4.1 | Supabase project setup (Auth, Postgres, Storage, Realtime) | RALPH | 100% |  | 2026-03-01 |  | 2026-03-08
1.4.2 | Authentication & role-based access (admin / alumni) | RALPH | 100% |  | 2026-03-09 |  | 2026-03-14
1.4.3 | Alumni roster & profiles database (RLS) | RALPH | 100% |  | 2026-03-15 |  | 2026-03-22
1.4.4 | Surveys & CHED GTS data model / evaluation | RALPH | 100% |  | 2026-03-23 |  | 2026-04-05
1.4.5 | Events, Jobs, Forum, Messaging backends | RALPH | 100% |  | 2026-04-06 |  | 2026-04-25
1.4.6 | Announcements + email delivery services | RALPH | 100% |  | 2026-04-26 |  | 2026-05-02
1.4.7 | Notifications (in-app, Web Push / FCM) | RALPH | 80% |  | 2026-05-03 |  | 2026-05-12
1.4.8 | Audit logging service | RALPH | 100% |  | 2026-05-13 |  | 2026-05-16
1.4.9 | Edge Functions (contact verify, exports, DSS helpers) | RALPH | 100% |  | 2026-05-17 |  | 2026-05-28
1.4.10 | Program Insights (DSS) server evaluation & rules | RALPH | 100% |  | 2026-06-01 |  | 2026-06-20
1.4.11 | Reports / analytics query layer | RALPH | 100% |  | 2026-06-21 |  | 2026-07-05
1.5 | Cross-cutting Delivery
1.5.1 | Admin UI/UX redesign (shared design system) | RALPH | 100% |  | 2026-09-06 |  | 2026-10-19
1.5.2 | Web hosting & release builds (Chrome / Hosting) | RALPH | 50% |  | 2026-10-20 |  | 2026-11-15
1.5.3 | System documentation & user/admin guides | RALPH | 70% |  | 2026-10-01 |  | 2026-11-30
1.6 | Testing and Quality Assurance
1.6.1 | Bugs fixes & optimization | RALPH | 70% |  | 2026-08-01 |  | 2026-11-30
1.6.2 | Automated tests (unit / widget / regression SQL) | RALPH | 80% |  | 2026-08-01 |  | 2026-11-15
1.7 | Project Implementation
1.7.1 | App / web deployment |  | 30% |  | 2026-12-01 |  | 2026-12-05
1.7.2 | Post-launch monitoring |  | 0% |  | 2026-12-06 |  | 2026-12-10
1.7.3 | User guide / manual turn-over |  | 20% |  | 2026-12-08 |  | 2026-12-12
1.7.4 | Project closure |  | 0% |  | 2026-12-13 |  | 2026-12-13
1.7.5 | Project acceptance |  | 0% |  | 2026-12-13 |  | 2026-12-13
| VALIDATED BY: |  | NOTED BY:
| LUTHERLY Q. BONGCAWEL, MIT |  | JUBILEE S. DAGA-ANG, MIT
| Capstone Adviser |  | IT Program Chairperson

## Testing
AESS System Development Testing
| Project Completion |  |  |  |  | Project Start: | 2025-03-01
[6 empty] | Display Week: | 2
TASK No. | ACTIVITY | ASSIGNED TO | PROGRESS | SUPPORT FEEDBACK | START | DAYS | END
1 | Project Initiation
2 | Testing and Quality Assurance — AESS
2.1 | Alumni Portal Testing
2.1.1 | Authentication (Login / Register / Forgot Password) testing | RALPH | 100%
2.1.2 | Alumni eligibility & registration testing | RALPH | 100%
2.1.3 | Onboarding wizard testing | RALPH | 100%
2.1.4 | Home dashboard testing | RALPH | 100%
2.1.5 | Events (RSVP / comments) testing | RALPH | 100%
2.1.6 | Tracer & Surveys (CHED GTS) testing | RALPH | 100%
2.1.7 | Job board testing | RALPH | 100%
2.1.8 | Community Forum testing | RALPH | 100%
2.1.9 | Messaging testing | RALPH | 100%
2.1.10 | Announcements testing | RALPH | 100%
2.1.11 | Profile & Alumni ID card testing | RALPH | 100%
2.1.12 | Feedback & AI Assistant testing | RALPH | 80%
2.1.13 | Notifications testing | RALPH | 70%
2.2 | Admin Portal Testing
2.2.1 | Admin dashboard & navigation testing | RALPH | 100%
2.2.2 | Alumni Directory / member detail testing | RALPH | 100%
2.2.3 | Surveys editor / responses / export testing | RALPH | 100%
2.2.4 | Reports & Analytics testing | RALPH | 100%
2.2.5 | Program Insights (DSS) workflow testing | RALPH | 100%
2.2.6 | Events / Announcements / Forum moderation testing | RALPH | 100%
2.2.7 | Jobs management testing | RALPH | 100%
2.2.8 | Messages / Feedback / Archives testing | RALPH | 100%
2.2.9 | Activity logs & permissions testing | RALPH | 100%
2.2.10 | CHED GTS PDF export testing | RALPH | 100%
2.3 | Backend & Platform Testing
2.3.1 | Supabase Auth / RLS testing | RALPH | 100%
2.3.2 | Roster & profiles database testing | RALPH | 100%
2.3.3 | Surveys / CHED GTS backend testing | RALPH | 100%
2.3.4 | Events / Jobs / Forum / Messaging backend testing | RALPH | 100%
2.3.5 | Announcements & email delivery testing | RALPH | 80%
2.3.6 | Notifications (push) testing | RALPH | 70%
2.3.7 | Audit logging testing | RALPH | 100%
2.3.8 | Edge Functions testing | RALPH | 80%
2.3.9 | DSS evaluation / rules testing | RALPH | 100%
2.4 | Bugs Fixes & Optimization | RALPH | 70%
2.5 | Project Implementation
2.5.1 | App / web deployment |  | 30%
2.5.2 | Post-launch monitoring |  | 0%
2.5.3 | User guide / manual turn-over |  | 20%
2.5.4 | Project closure |  | 0%
2.5.5 | Project acceptance |  | 0%
VALIDATED BY:
LUTHERLY Q. BONGCAWEL, MIT
Capstone Adviser

## UAT
AESS — User Acceptance Testing log
Record defects and change requests found during UAT. Cleared unrelated project (MABISA) placeholders.
AESS UAT
NO. | USER | MODULE | TYPE | ISSUE | TARGET DATE
1 |  | Module > Screen > Example | Bug |  | 2024-12-08
2 |  |  | New
3 |  |  | New
4 |  |  | New
5 |  |  | New
6 |  |  | New
7 |  |  | New
MIGRATION / DATA NOTES
NO. | USER | MODULE | TYPE | ISSUE | TARGET DATE

## Database Design
AESS DATABASE AREAS
| TABLE / AREA | DOMAIN | CONSTRAINTS / NOTES | WBS
| users / auth | Core | Supabase Auth + users role | 1.4.2
| alumni_roster / profiles | Core | Official graduates, eligibility | 1.4.3
| surveys / responses / CHED GTS | Core | Tracer waves & answers | 1.4.4
| events / rsvp / comments | Community | Campus events | 1.4.5
| jobs / job_interest | Careers | Job board | 1.4.5
| forum_topics / replies / tags | Community | Moderated discussion | 1.4.5
| messages / attachments | Community | Admin-alumni chat | 1.4.5
| announcements / deliveries | Community | Email + in-app | 1.4.6
| notifications | Platform | In-app / push tokens | 1.4.7
| audit_logs | Platform | Admin accountability | 1.4.8
| dss_flags / rules / interventions | Insights | Program Insights DSS | 1.4.10
| feedback | System | Alumni feedback tickets | 1.3.13
| archives | System | Archived content refs | 1.3.12
| storage buckets | Platform | Images / PDFs / exports | 1.4.1